## Slide 1: WRAP TSC/Co-Chairs Call Workplan Progress Update August 29, 2018
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2
Tribal Data Work Group

## Slide 3: Tribal Data Work Group
Co-Chairs: Kris Ray (Colville Tribes) and Emma Ruppell (Bishop Paiute Tribe)
Call Schedule: as needed
Website:
Current Tasks/Projects
  Working on the Tasks in the 2018 to 19 workplan
  Data analysis
  Outreach

## Slide 4: Status Report for Tribal Data Work Group
Approach
  Reviewed current workplan
  Identified work tasks
  Scheduled tasks to begin
Status
  Reviewing proposal from ITEP for data analysis and outreach material development
Milestones – Most products completed within 10 week of contract
Coordination and Next Steps – TDWG calls and keep other WG informed

## Slide 5
Fire and Smoke Work Group
and

## Slide 6: Fire & Smoke Work Group
Co-Chairs: Sara Strachan, Josh Hall
Call Schedule: bimonthly, more frequent calls if/as needed
Website: http://www.wrapair2.org/FSWG.aspx
Current Tasks/Projects
  2014 WRAP FETS data review
  National 2016 Emissions Modeling Platform – Fires WG support for WRAP region
  Steady update/maintenance work on WRAP FETS website and database

## Slide 7: Status Report for Fire & Smoke Work Group
  Fire season is underway…!
  Approach: 4 tasks in 2018-19 by Air Sciences, Inc. (contracted work)
    evaluation of the 2014 NEI, evaluation of adjustments for sensitivity testing, and evaluation of usefulness of 2016 EPA inventory effort for understanding the role of fire;
    using year specific inventory to develop inventory representative of 5-year baseline;
    scaling the representative inventory for sensitivity testing; and
    updating the Fire Emissions Tracking System (FETS)
  Status
    FSWG calls scheduled August 27, October 4, and December 13
  Milestones
    Align with modeling input file milestones
  Coordination and Next Steps
    September 24th call

## Slide 8: Status Report for Fire & Smoke Work Group
2014 WRAP FETS/Fire NEI data review
  Approach
    Build an evaluation framework for states/tribes to review inventory
    Follow up individually as needed to solicit feedback
    Summarize results in a memorandum with recommendations for holistic inventory updates
  Status
    2014 Fire NEI Evaluation Tool: http://35.163.196.248/2014_fire_nei_eval
    Need to obtain v2 Fire NEI data: done
    Matt providing a 1 page explanation to accompany tool for group members and a historical/contextual document (due before Aug. 27th call so group has time to digest before call)
  Milestones
    August 2018 – finalize eval framework: done
    Q3 2018 – obtain feedback from states/tribes
    Expect to have recommendations by 11/1/18
  Coordination and Next Steps
    Introduce eval tool to group
    Receive feedback

## Slide 9: Status Report for Fire & Smoke Work Group
2016 WRAP FETS/Fire NEI data review
  Approach
    Participate in fire workgroup process
    Apply 2014 evaluation framework to beta version (2016b)
    Draft recommendations for national fire workgroup based on evaluation
  Status
    Monthly fire workgroup calls and coordination
  Milestones
    Q3 2018 – apply eval framework to 2016b
    Expect to have recommendations by December 2018
  Coordination and Next Steps
    Continue participation in fire workgroup monthly calls

## Slide 10
Oil and Gas Work Group

## Slide 11: Oil and Gas Work Group
Co-Chairs: Amanda Brimmer, Mark Jones, and Darla Potter
Call Schedule:
  OGWG - 2nd Tuesday, every other month @ noon MT
    October 9, 2018
    December 11, 2018
  OGWG Project Management Team (PMT) Calls – as needed
Website: https://www.wrapair2.org/OGWG.aspx
Current Tasks/Projects
  Road Map Phase II:
    Task 1: 2014 Base Year O&G Emissions Inventory
    Task 2: 2028 Forecast O&G Emissions Inventory (based on 2023)
      will include on-the-books (OTB) and on-the-way (OTW) controls

## Slide 12: Status Report for Oil and Gas Work Group
Task 1: 2014 Base Year O&G Emissions Inventory | 
Approach: Contractor (Ramboll) performing work on following tasks: | Status/Deliverables
Inventory Compilation, Reconciliation, Data Gaps | Spreadsheet* + WG Discussion 8/14
2014 O&G Activity | Spreadsheet* + WG Discussion 8/14
Identify Emission Factors and Speciation Profiles for Oil and Gas Sources | PMT Discussion 8/20
State and industry survey | PMT Discussion 8/20
Technical Improvements and Reporting | PMT Discussion 8/20
SMOKE-ready Emission Inventory Files | No work yet
Milestones: | 
Sept. 2018 – Literature review PowerPoint | 
Oct. 2018 – Survey finalized to send out | 
Apr. 2019 – SMOKE-ready 2014 O&G emissions inventory files | 
Coordination and Next Steps: | 
Assistance needed from States to complete survey (coordinate with local industry if needed) | 
OGWG and Project Management Team (PMT) review of draft work products | 
* Posted on OGWG webpage

## Slide 13: Status Report for Oil and Gas Work Group
Task 2: Forecast 2028 (OTB & OTW Controls) Oil & Gas Emissions Inventory | 
Approach: Contractor (Ramboll) performing work on following tasks: | Status
Identify historic growth, supply, demand, and production decline | No update
Identify a Range of Forecast Year Oil and Gas Scenarios | “
Identify Rule Penetration and Effectiveness for Oil and Gas Sources: National, State, Local, Tribal | “
Implement Regionally-Consistent 2028 Forecast (OTB & OTW controls) Emissions Inventory | “
SMOKE-ready Emission Inventory Files | “
Milestones: | 
May 2019 – Final Report | 
June 2019 – SMOKE-ready 2028 O&G emissions inventory files | 
Coordination and Next Steps: | 
OGWG and Project Management Team (PMT) review of draft work products | 

## Slide 14
Regional Technical Operations Work Group

## Slide 15: RTOWG Work Group
Co-Chairs:
  Gail Tonnesen (EPA R8)
  Kevin Briggs (CO CDPHE)
  Mike Barna (NPS ARD)
Call Schedule:
  Next call: 9/20/18
  RTOWG co-chairs participating in other workgroup calls
Website:
  http://www.wrapair2.org/RTOWG.aspx

## Slide 16: Status Report for RTOWG
RTOWG call, 8/18/18
  Coordination of monthly phone call between WRAP RTOWG and EPA OAQPS to discuss issues relevant to air quality modeling in the western US, Gail Tonnesen
  Review of "model year representative" study, Till Stoeckenius (Ramboll)
  "Supporting the use of satellite data in haze planning, a 2018-2019 NASA HAQAST Tiger Team", Arlene Fiore (Columbia U. - LDEO)
  “Using Satellite Data to Improve Background Ozone Estimates: Outlook for a New Project from NASA’s HAQAST”, Jessica Neu (NASA JPL)

## Slide 17: Status Report for RTOWG
Example’s from Arlene’s presentation
HAQAST Regional Haze Tiger Team - "listening session" for Western U.S. planning, 8/28/18

## Slide 18: Status Report for RTOWG
Example from Jessica’s presentation

## Slide 19
Regional Haze Planning Work Group

## Slide 20: WRAP TSC/Co-Chairs Call Workplan Progress Update August 29, 2018
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 21
Co-Chairs: Tina Suarez-Murias (CARB) & Jay Baker (UT DEQ)
Call Schedule: October 2, 2018 noon – 2:00 Mountain Time
  1st Tuesday every even month
Website: https://www.wrapair2.org/RHPWG.aspx
Current Tasks/Projects – all related to State Regional Haze SIP preparation (2018-2019)
  Review and provide feedback on the Internal & External Commitments and Schedule document
  Evaluated alternatives to EPA guidance metric for selecting Most Impaired Days (MID)
  Confirmed 2014 NEI v2 as base year inventory and refining state-by-state for modeling consistency
  Drafted Screening Tool protocol to identify potential sources for four-factor analysis
  Beta-testing shared Database “TSSv.2” for Monitoring, Emissions, and Modeling
  State–State, State–FLM, State–Tribes, and Public Communication and Outreach
  Coordinate with other Work Groups and WRAP Technical Steering Committee
  Conference Call notes on website with presentations and links
Regional Haze Planning Work Group
Notes: The Work Group is lengthening its bimonthly call to 2 hours. As a matter of necessity, the large Work Group is evolving into a classroom where everyone is brought up to speed for SIP preparation.
The smaller subcommittees and other Work Groups and contractors are developing products, tools, and deliverables needed to write the SIPs.
As we start to roll out some of the tools, etc. we may have additional meetings, depending on the complexity of the items we need to explain.

## Slide 22
RHPWG Subcommittees | Leads | Call Schedule | Website
Monitoring Data and Glide Path | Ryan Templeton (AZ DEQ) | every two weeks, on Thursdays @ 1-2 Mountain | https://www.wrapair2.org/RHP_DataGlide.aspx
Shared Database | Cindy Hollenberg (NM NMED) | every month, 2nd Thursday @ 10-11 Mtn 4th Thursday @ 2:30-3:30 Mtn Aug. 30 @ 10:00 – 11:00 Mtn | https://www.wrapair2.org/RHP_SharedDB.aspx
Control Measures | Curt Taipale (CO DPHE) | every month, fourth Wednesday @ 10-11 Mountain | https://www.wrapair2.org/RHP_Control.aspx
Emissions Inventory and Modeling Protocol | Farren Heron-Thorpe (WA DOE) | every month, last Thursday @ noon-1 Mountain | https://www.wrapair2.org/RHP_InvMod.aspx
Consultation & Coordination | Rebecca Harbage (MT DEQ) | every month, second Tuesday @ 2-3 Mountain | https://www.wrapair2.org/RHP_ConsCo.aspx
Regional Haze Planning Work Group
Subcommittees
Notes: The only change is that the shared Database committee is meeting more frequently in order to provide more timely feedback to the TSS v.2 contractor.

## Slide 23: Regional Haze Planning Work Group Monitoring Data & Glide Slope Status Report
Approach
  Evaluate proposed EPA tracking metric compared to alternative extreme episodic event (E3) thresholds and alternatives for selecting the 20% Most Impaired Days (MID)
  Set up Excel spreadsheet and R code analysis to test variables
  Each State can use these tools to analyze their IMPROVE sites using FED dataset
Status
  Identified 26 representative IMPROVE sites and prepared evaluation data for wider review
  https://azdeq.sharefile.com/d-s3e0afe94b844e70a
  Prepared draft list of alternative approaches to MID metric with pros and cons for each
  Reviewed IWDW 2011 modeling-monitoring performance to learn about “IMPROVE- adjusted” data
Milestones
  Preparing documentation of the analytical approaches evaluated
  Contractor to prepare report documenting data patching and data substitution
  Representative site analysis link made available to RHPWG for reviewing and use
Coordination and Next Steps and Tasks
  Present findings to TSC and then to SIP/TIP writers through RHPWG
  Draft Report for feedback from RHPWG (all states, FLMs, tribes, EPA)
  Evaluate changes to redo Baseline and adjust 2064 Natural Conditions
  Consider tools that might help differentiate natural and anthropogenic sources
Notes: The Monitoring Subcommittee encourages all to review the R and Excel tools they have developed to compare methods to calculate Most Impaired Days for each state’s IMPROVE monitors.
Next on the agenda is reviewing Natural Conditions and redoing the baseline.
Any recommendation for a single MID process will be presented to the TSC and then the Regional Haze Work Group.
Coordinating with the Shared Database Subcommittee.

## Slide 24: Regional Haze Planning Work Group Control Measures Status Report
Approach
  Develop Protocols for States to use to target emissions reductions from Non-Mobile Anthropogenic Sources within their State
  Develop means to demonstrate these reductions improve visibility in Class I Areas (e.g. 0.5 deciview impact)
Status
  Interpret EPA proposed guidance for 80% of non-mobile anthropogenic sources (facility/unit/source category)
  Propose Q/d threshold screening tool (e.g. Emissions/Distance from Class I Area >10)
  Utilize WRAP/WEP and existing Land Use Maps from TSS v.1 to identify potential impacting sources
Milestones
  Develop and circulate schedule for States’ input to other Work Groups and contractors (pending)
  Drafted potential screening techniques protocol for western states (Subcommittee review by September 14, 2018)
Coordination and Next Steps
  In October, circulate Screening Techniques Protocol as working draft to states for use as guidance selecting “target sources”
  Review four-factor methods and options
  Work with other Work Groups on multi-year emissions averaging if needed for cost-benefit analysis or modeling
  Coordinate with Oil & Gas Work Group differentiating Area Source Emissions vs. Stationary Source facilities with multiple units
  Determine needs for contractor assistance
Notes: -Control Measure subcommittee is reviewing a draft screening techniques protocol. Although subcommittee members are adding to it now, it will remain a Working Draft when released. It will describes a menu of techniques that states can use to select sources for which a four-factor analyses can be applied.
-For screening to identify potential sources for further review states can use:
  Existing tools, such as the existing Land Use maps from the Causes of Haze, accessible through the TSSv.1 webpage
  Future Weighted Emissions Potential or WEP, that results from modeling
  Q/d or emissions over distance – which may be more or less than 10, depending on the state geography
-Next steps are to work on the four-factor method and differentiate between point and area sources.

## Slide 25: Regional Haze Planning Work Group Emissions Inventory & Modeling Protocol Status Report* *last meeting July 26; next meeting August 30
Approach
  Collect and collate emissions data from all states (2014 and future forecasts)
  Photochemical modeling for CONUS western states
Status
  All states have verified 2014 data, some still making adjustments
  Photochemical modeling contract in development
Milestones
  Identifying categories needing further attention (e.g. unpaved road dust, unreported minor sources)
  Considering categories to be grouped for source apportionment (e.g. residential woodsmoke)
Coordination and Next Steps
  Set deadline to grid out 2014 inventory for regional photochemical modeling
  Work with RTO Work Group to secure contractor for baseline and future year modeling
  Get 2014 data from Oil & Gas and Fire & Smoke Work Groups
  Coordinate with Fire & Smoke Work Group on multi-year averages to use for future year modeling
Notes: This subcommittee has not met since the last TSC meeting.
Members are chasing down emissions inventories from states that have not confirmed or changed their 2014 inventories
Several members are also on the RTO Work Group and are working on modeling protocols with that group.

## Slide 26: Regional Haze Planning Work Group Shared Database Status Report
Approach
  Assure that publically accessible database has useful information for states to use in SIP preparation
  Work with CIRA contacts to share state needs and evaluate design of TSS v.2
Status
  In early stages of development, with SC member reviews ongoing
  Comments compiled for CIRA collaborator’s response
Milestones
  Reviewing latest features of TSS v.2 (including comparison of haziest and most impaired days)
  Anticipate TSS v.2 progress report in October 2018
Coordination and Next Steps
  Developing a trend tool to allow states to assess 2000-2016 monitoring data trends with MID relative to revised Glide Path
  Assist with development of Glossary for TSS v.2
  Coordinating with Monitoring Subcommittee regarding the visualization tool and will coordinate with Emissions and Modeling subcommittee regarding additional functionality (beyond TSSv1), if any
Notes: The Shared Database Subcommittee is working with the contractors at Colorado State on Technical Support System v2. with the hope of presenting it to the Regional Haze Work Group at the October 2 Conference Call of the Regional Haze Work Group.
They caution that the algorithms behind the display might change the final values displayed as the Monitoring and Glide Path subcommittee and the contractors verify the input values.
Some data patching and substitution may be needed at some monitors, if they do not have a complete year that is critically needed.

## Slide 27: Regional Haze Planning Work Group Consultation and Coordination Status Report
Approach
  Recommend protocol for State – State, State – Local Air Agency, and State – FLM consultation and for State – Tribes coordination
  Potential ideas for future Communication and Outreach with public
Status
  Collecting information from all states to update list of contacts at all agencies and tribes for purposes of working on SIP issues and for formal review of draft State SIPs
  Drafting White Paper that recommends occasions for informal consultation during SIP development
Milestones
  Contact List nearly complete
  General Contract for $25,000 for all subcommittees includes formal consultation requirements as they relate to each state’s public review procedures
Coordination and Next Steps
  Consider developing protocol for state-to-state negotiation regarding upwind state reductions
  Provide additional information for state-local air agency coordination
Notes: The Consultation and Coordination Subcommittee is completing their list of contacts and working on a white paper that will link consultation to key points in the SIP development process.
New contacts from the Forest Service and the Fish and Wildlife Service and EPA have just joined the Subcommittee.

## Slide 28
End of Workplan Progress Update