WRAP Work Group and Subcommittee

Estimated Staffing Commitments

# Technical Steering Committee (meets monthly)

* Committee Co-Chairs **20-60 hours/month/person**
* Committee Members **2-4 hours/month/person**

# Fire and Smoke Work Group (meets monthly)

* Work Group Co-Chairs **4-40 hours/month/person**
* Work Group Members **2-8 hours/month/person**

# Oil and Gas Work Group (meets in even months)

* Work Group Co-Chairs **8-16 hours/month/person**
* Work Group Members **2-4 hours/month/person**

# Regional Technical Operations Work Group (meets monthly)

* Work Group Co-Chairs **8-24 hours/month/person**
* Work Group Members **4-12 hours/month/person**

# Tribal Data Work Group(meets as needed, generally monthly)

* Work Group Co-Chairs **2-8 hours/month/person**
* Work Group Members **1-4 hours/month/person**

# Regional Haze Planning Work Group (meets in even months)

* Work Group Co-Chairs **16-24 hours/month/person**
* Work Group Members **3-5 hours/month/person**

# Regional Haze Subcommittees

## Monitoring and Glide Path Subcommittee (meets every 2 weeks)

* **Task 1 Monitoring Data Analysis** (through December 2018)
	+ Subcommittee Lead **40+ hours/month/person**
	+ Subcommittee Members **4-40 hours/month/person**

## Emissions Inventory and Modeling Protocol Subcommittee (meets monthly)

* **Task 2 Emissions Inventory** (through December 2018)
* **Task 3 Air Quality Modeling** (through 1st Q 2020)
* **Task 4 Analyzing Future Year Modeling Results** (through 1st Q 2020)
	+ Subcommittee Lead **8-12 hours/month/person**
	+ Subcommittee Members **2-6 hours/month/person**

## Control Measures Subcommittee (meets monthly)

* **Task 5 Control Measures Analysis** (through December 2019)
	+ Subcommittee Lead **8-16 hours/month/person**
	+ Subcommittee Members **4-8 hours/month/person**

## Shared Database Subcommittee (was meeting monthly, now twice a month)

* **Task 7 Technical Support System TSS.v2** (through 1st Q 2020)
	+ Subcommittee Lead **12-16 hours/month/person**
	+ Subcommittee Members **3-5 hours/month/person**

## Consultation and Coordination Subcommittee (meets monthly)

* **Task 8 State Planning and Adoption Process** (through 3rd Q 2021)
	+ Subcommittee Lead **8-12 hours/month/person**
	+ Subcommittee Members **2-4 hours/month/person**