## Slide 1: Monthly Update on 2018-2019 WRAP Workplan August 28th, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last Month
  TDWG & EN3 review & comments on CC Framework
  EN3 finalized, distributed Emissions Inventories Evaluation (Tribal Oil & Gas)
Workplan Tasks for the Next Two Months
  EN3 review & comments on CC Framework; feedback to RHPWG
  Complete finalization by consensus of EI Evaluation (Tribal Oil & Gas)
  Plan 2nd webinar
  Send TDWG participation letter – via WRAP staff/WRAP web service
  Create “active tribes” section of tribal contacts list based on participation letter responses

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  Review of CC Framework with C&G SC
Workplan Coordination Needed over the Next Two Months
  Submit EN3’s final comments to RHPWG/Ramboll either direct or via TDWG
  Tribal contacts list – format & arrange for state planning use via RHPWG
  Distribute EN3’s EI Evaluation to OGWG
  OGWG – webinar possibility?

## Slide 5: Fire and Smoke Work Group

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Distributed SMP survey to state and tribal contacts
  New, small contract with OAQPS to help with 2017 Fire NEI
    Distributed 2017 NEI fire activity survey to WRAP members
    Reaching out to additional members individually
Workplan Tasks for the Next Two Months
  Collect, collate, and submit to OAQPS fire activity data for 2017 NEI
  Collect and collate data for SMP survey
  Add SMP survey data to WRAP map
  Work on Future Fire Scenarios EI for sensitivity runs

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  No workgroup calls since last TSC meeting
Workplan Coordination Needed over the Next Two Months

## Slide 8: Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress Over the Last Month
  OGWG and Project Management Team (PMT) review and feedback
  Baseline Inventory – Complete
    Deliverables on WRAP OGWG website
      Baseline Inventory: technical memo, spreadsheet, gas profiles
      Survey: Data Collection Synthesis Memo, Complete Survey, Fleet turnover & controls-focused survey
      Base Case: 2014 base case v1 emissions inventory spreadsheet, 2014 oil and gas activity spreadsheet
    SMOKE-inputs developed for WRAP Modeling and 2016 Emissions Platform Collaborative
  Forecast Scenarios – Underway
Workplan Tasks for the Next Two Months
  Task 2: Forecast 2028 Inventory (OTB & OTW controls) – September / October
    “Continuation of Historical Trends” Scenario including controls analysis (September)
    “Reduced Legacy Well Activity” and “Increased Horizontal Well Activity” Scenarios (October)
  Task 3: Forecast 2028 Inventory (Additional Reasonable controls) – End of 2019
    Single forecast scenario and integrate OGWG survey data
  Task 4: Agency Program Review Task – End of 2019

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring Over the Last Month
  August 6 & 20 – Project Management Team Calls
    Coordinate and PMT feedback with Ramboll
  August 9 & 19 – Colorado 2014/2016 O&G EI Calls
Workplan Coordination Needed Over the Next Two Months
  Sept. 3 & 17, Oct. 6 – Project Management Team Calls
  October 8 – OGWG Bi-Monthly Call
  OGWG and PMT review and feedback on draft work products
    Sept. 6-16 Forecast “Continuation of Historical Trends” Scenario Draft Report & Spreadsheet
  Coordination with RHPWG Control Measures Subcommittee
Coordination (External to WRAP) Occurring / Needed
  EPA’s 2016 Modeling Platform Collaborative – availability of OGWG baseline & future inventory
  2017 NEI – account for inventory improvements

## Slide 11: Regional Technical Operations Work Group

## Slide 12: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  Coordination with contractor on modeling progress for 2014v2
    Calls on 8/1 and 8/5
  Updates to emission inventory for 2014v2 shakeout simulation
    Replacement of CA emissions
    Webinar on 8/15
  Bi-weekly RTOWG co-chair coordination calls

## Slide 13: Workplan Progress by RTOWG
Workplan Tasks for the Next Two Months
  Revised schedule for “Phase III” modeling deliverables

## Slide 14: Workplan Coordination Activities by RTOWG
Workplan Coordination Occurring over the Last Month
  HAQAST Regional Haze call on 8/5
  RTOWG monthly call on 8/6
  Participation on RHPWG (8/6) and OGWG (8/13) calls
  HAQAST Background Ozone call on 8/14
Workplan Coordination Needed over the Next Two Months
  RTOWG calls: 9/10, 10/15, 11/12
  Emission inventory updates for 2028: mobile, EGU’s
  Coordination calls with Ramboll for completion of Phase III modeling deliverables by October
  Preparation of representative baseline emissions

## Slide 15: Regional Haze Planning Work Group

## Slide 16
Workplan Progress and Coordination over the Last Month
  Coordinated with C&GP, EI&MP Subcommittees to present task updates on monthly call (August 6, 2019)
  Coordinated with RTO Workgroup on Regional Haze modeling progress and an updated modeling timeline
  Coordinated with NPS about the Q/d work they sent to states
Workplan tasks and Coordination for the Next Two Months
  Final review of and consensus on the WRAP Communication Framework (September)
  Development of Regional Haze in the West Storyboard
  Coordinate ongoing discussions of controls and modeling – both require states to consult with sources
  Next milestone webinar planned for October 3
Workplan Progress & Coordination by Regional Haze Planning Work Group

## Slide 17: Workplan Progress by Control Measures Subcommittee
Workplan Progress over the Last Month
  Discussed the relationship between state-specific point source thresholds and the challenges for considering O&G Area Sources in the 4-factor review process
  State-specific updates on four-factor work
Workplan Tasks for the Next Two Months
  Plan to discuss the evaluation of mobile sources, other area sources and how to analyze EGU retirements on the next call scheduled for Sept 23rd

## Slide 18: Workplan Coordination Activities by Control Measures Subcommittee
Workplan Coordination Occurring over the Last Month
  Oil & Gas work group – forecasting OTB/OTW controls
Workplan Coordination Needed over the Next Two Months
  Continue to coordinate with O&G work group and Emission Inventory Subcommittee on emission forecasts.

## Slide 19: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress over the Last Month
  Task 6.3: Develop New Materials
    D) Storyboard – Haze in the West
      Team has drafted an outline of the storyboard. Looking to hire a contractor to produce a mock-up that can be presented to the states. Aiming to present on the Fall Periodic Webinar.
    E) Webinar Presentations to States
      Next milestone webinar targeting late-September to early-October 2019
  Task 7.1: Review TSS v1 for Priority Needs
    Coordinating call with RTOWG to discuss “TSS Priorities” document feedback
  Task 7.2: Coordinate and Review TSS v2 Monitor Data Tool Development
    Monthly presentations on new metrics and tools from CIRA on TSS progress
  Need additional discussions on how to "freeze" the TSS version of the IMPROVE base data and RHR/Impairment metrics for planning period
  Task 8.2: Establish Consultation-Coordination Framework
    Joint call by the TDWG and C&GP Sub to review comment on latest draft of the Consultation and Coordination Framework
Workplan Tasks for the Next Two Months
  Task 1.2: Analyze monitor data trends
    Brandon (Montana) and ARS presented the results of the trend analysis and natural conditions alternative ideas project on August 27 1-2:30 MDT.
  Task 6.3: Develop New Materials
    B) Glossary & C) FAQs
      Need to finish review of FAQ’s and elevate it to RHPWG for further review

## Slide 20: Workplan Coordination Activities by Coordination and Glide Path Subcommittee
Workplan Coordination Occurring over the Last Month
  The subcommittee coordinated with the following entities:
    TDWG – Finalizing edits to the Consultation-Coordination Framework document
Workplan Coordination Needed over the Next Two Months
  RTOWG – Coordination on Natural Conditions Project findings and opportunities to model outcomes for future planning periods.
  RTOWG – TSS Priorities for Modeling/EI

## Slide 21
Workplan Progress by EI&MP Subcommittee
Workplan Progress over the Last Month
  Send out memo describing Shakeout v2 updates
Workplan Tasks for the Next Two Months
  Procedural guidance for preparing OTB/OTW emissions updates
  OTB/OTW emissions to be submitted by states in August

## Slide 22: Workplan Coordination Activities by EI&MP Subcommittee
Workplan Coordination Occurring over the Last Month
  O&G v2 emissions will come from contractor based on state comments
Workplan Coordination Needed over the Next Two Months
  v2 shakeout, representative baseline, and OTB modeling scenarios require coordination as needed with O&G WG, contractor, Fire & Smoke WG,
  Coordinate with C&GP subcommittee to provide guidance to states on what is needed from them for the different modeling scenarios

## Slide 23
End of Workplan Progress Update