## Slide 1: Monthly Update on 2018-2019 WRAP Workplan September 25th, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last Month
  EN3 finalized, distributed to TDWG final tribal contacts list with “active tribes”
  Emissions Inventories Evaluation- Tribal Oil & Gas final report (August)
Workplan Tasks for the Next Two Months
  Finalize EI Evaluation (Tribal Oil & Gas) – distribution to subject tribes, OGWG
  WRAP webpage/maps, TSS v2, IWDW webinar with ITEP
  Send TDWG participation letter – via WRAP staff/WRAP web service

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  Communications Framework finalized
  Tribal contacts list finalized
Workplan Coordination Needed over the Next Two Months
  Distribute EN3’s EI Evaluation to OGWG (2 week turnaround)

## Slide 5: Fire and Smoke Work Group

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Distributed SMP survey to state and tribal contacts – still gathering info
  Small contract with OAQPS to help with 2017 Fire NEI – completed
    Distributed 2017 NEI fire activity survey to WRAP members
    Reaching out to additional members individually
    Delivered info to EPA OAQPS
Workplan Tasks for the Next Two Months
  Deliver final representative baseline fire EI to modeling group
  Collect and collate data for SMP survey
  Add SMP survey data to WRAP map
  Work on Future Fire Scenarios EI for sensitivity runs

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  One RBFFS conference call since last TSC call
  One FSWG call since last TSC call
Workplan Coordination Needed over the Next Two Months

## Slide 8: Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress Over the Last Month
  OGWG and Project Management Team (PMT) review and feedback
  Baseline Inventory – Complete
    Revised Final Report and Inventory Spreadsheet
      Completely replaces the previously posted July 2019 report and spreadsheet
        CO O&G emissions based on new inventories provided by CDPHE & Southern Ute Indian Tribe
        Williston Basin casinghead gas emissions correction of biased low based on EPA O&G Tool inputs
    SMOKE-inputs developed for WRAP Modeling and 2016 Emissions Platform Collaborative
  Forecast Scenarios – Underway
Workplan Tasks for the Next Two Months
  Task 2: Forecast 2028 Inventory (OTB & OTW controls) – September / October
    “Continuation of Historical Trends” Scenario including controls analysis (September)
    “Reduced Legacy Well Activity” and “Increased Horizontal Well Activity” Scenarios (October)
  Task 3: Forecast 2028 Inventory (Additional Reasonable controls) – End of 2019
    Single forecast scenario and integrate OGWG survey data
  Task 4: Agency Program Review Task – End of 2019

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring Over the Last Month
  September 3 & 17 – Project Management Team Calls
    Coordinate and PMT feedback with Ramboll
Workplan Coordination Needed Over the Next Two Months
  Oct. 1 – OGWG Webinar Midterm Update
  October 8 – OGWG Bi-Monthly Call
  Oct. 15 & 30 – Project Management Team Calls
  OGWG and PMT review and feedback on draft work products
    Sept. 20 – Oct. 1 Forecast “Continuation of Historical Trends” Scenario Draft Report & Spreadsheet
  Coordination with RHPWG Control Measures Subcommittee
Coordination (External to WRAP) Occurring / Needed
  EPA’s 2016 Modeling Platform Collaborative – availability of OGWG baseline & future inventory
  2017 NEI – account for inventory improvements

## Slide 11: Regional Technical Operations Work Group

## Slide 12: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  Coordination with contractor on modeling progress for 2014v2
    Calls on 9/4 and 9/15
    Given delays in emission processing, eliminate some of the non-critical sensitivity runs
      MEGAN biogenic emissions
      Shortened (one month) fire plume rise evaluation
      CMAQ simulation (to compare with CAMx) deferred, but will be completed if time/$ allows
  Updates to emission inventory for 2014v2 shakeout simulation
    Reprocessing O&G emissions to fix error
    Re-mapping CMAQ dust and anthropogenic SOA precursor emissions to CAMx
  GEOS-Chem “natural conditions” run finished
  Representative Baseline EGU Emissions and Temporal Profiles
  Bi-weekly RTOWG co-chair coordination calls
  Reviewing EPA 2016 modeling TSD

## Slide 13: Workplan Progress by RTOWG
Workplan Tasks for the Next Two Months
  Finish updates to 2014v2 emissions and run CAMx
  Abbreviated fire plume rise sensitivity run
  GEOS-Chem “international contributions” run
  Feed the two GEOS-Chem runs (“natural conditions” and “international contributions”) to CAMx
  Broad-Based Anthro vs. Natural PM Source Apportionment
  Representative Baseline Emissions Modeling
  Representative Baseline PGM Modeling
  Dynamic Evaluation Scoping
  2028 Mobile Source Emissions Projections
  2028 PGM Modeling and Visibility Projections
  Analysis of EPA’s 2016 Beta-Prime Platform and 2028 Visibility Projections
Aiming to have 2028 simulations done
by end of 2019

## Slide 14: Workplan Coordination Activities by RTOWG
Workplan Coordination Occurring over the Last Month
  RTOWG monthly call on 9/10
  EPA RH Guidance Webinar 9/10
  Participation on Coordination & Glide Path Subcommittee (9/12)
  RTOWG modeling progress call (9/4 and 9/19)
Workplan Coordination Needed over the Next Two Months
  RTOWG calls: 10/15, 11/12
  ~weekly discussions with Ramboll to discuss modeling progress
  2016 model performance call with EPA 9/25

## Slide 15: Regional Haze Planning Work Group

## Slide 16
Workplan Progress and Coordination over the Last Month
  New Co-chair: David Stroh from North Dakota
  Final review of and consensus on the WRAP Communication Framework (September)
  Review of example 4-factor analysis by North Dakota
  Outreach and coordination with FSWG to complete Smoke Management Plan Survey
Workplan tasks and Coordination for the Next Two Months
  Next milestone webinar planned for October 3
  Review of EPA’s Regional Haze Guidance
  Development of Regional Haze in the West Storyboard
  Coordinate ongoing discussions of controls and modeling – both require states to consult with sources
Workplan Progress & Coordination by Regional Haze Planning Work Group

## Slide 17: Workplan Progress by Control Measures Subcommittee
Workplan Progress over the Last Month
  No call was held in August
  States continuing work on 4-factor analysis
Workplan Tasks for the Next Two Months
  Plan to discuss the evaluation of mobile sources, other area sources and how to analyze EGU retirements on the next call scheduled for Sept 23rd

## Slide 18: Workplan Coordination Activities by Control Measures Subcommittee
Workplan Coordination Occurring over the Last Month
Workplan Coordination Needed over the Next Two Months
  Continue to coordinate with O&G work group and Emission Inventory Subcommittee on emission forecasts.

## Slide 19: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress over the Last Month
  Discussion on status of Coordination Framework
  Review of TSS FAQ Document
  Initial discussion on TSS Glossary
Workplan Tasks for the Next Two Months
  Finish review of FAQ’s and elevate it to RHPWG for further review
  Come to consensus on if current TSS Glossary meets needs
  Revisit TSS Priorities document

## Slide 20: Workplan Coordination Activities by Coordination and Glide Path Subcommittee
Workplan Coordination Occurring over the Last Month
  The subcommittee coordinated with the following entities:
    RHPWG – Elevated Coordination Framework for Consensus
Workplan Coordination Needed over the Next Two Months
  RTOWG – Coordination on Natural Conditions Project findings and opportunities to model outcomes for future planning periods.
  RTOWG – TSS Priorities for Modeling/EI

## Slide 21
Workplan Progress by EI&MP Subcommittee
Workplan Progress over the Last Month
  Sent out memo describing Shakeout v2 updates
  Contractor finalizing Shakeout v2 simulations
  Sent out Procedural guidance for preparing OTB/OTW emissions updates
  Sent out EGU projection methodology and proposed mobile methods
Workplan Tasks for the Next Two Months
  Deliver Rep. Baseline emissions from states/locals to contractor
  Contractor to start Rep. Baseline simulations

## Slide 22: Workplan Coordination Activities by EI&MP Subcommittee
Workplan Coordination Occurring over the Last Month
  O&G v2 emissions will come from contractor based on state comments
Workplan Coordination Needed over the Next Two Months
  representative baseline, and OTB modeling scenarios require coordination as needed with O&G WG, contractor, and Fire & Smoke WG
  Coordinate with C&GP subcommittee to provide guidance to states on what is needed from them for the different modeling scenarios

## Slide 23
End of Workplan Progress Update