## Slide 1: Monthly Update on 2018-2019 WRAP Workplan October 30th, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last 2 Months* (Oct mtg cancelled)
  EN3 finalized, distributed to TDWG final tribal contacts list with “active tribes”
  Emissions Inventories Evaluation- Tribal Oil & Gas final report (august)
Workplan Tasks for the Next Two Months
  Finalize EI Evaluation (Tribal Oil & Gas) – distribution to subject tribes, OGWG
  Planning call for WRAP webpage/maps, TSS v2, IWDW webinar with ITEP
  Send TDWG participation letter – via WRAP staff/WRAP web service

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  1st planning call for webinar
Workplan Coordination Needed over the Next Two Months
  Distribute EN3’s EI Evaluation to OGWG (2 week turnaround)
  Webinar – planning calls, webinar scheduled for Dec 4th, 10 am MST

## Slide 5: Fire and Smoke Work Group

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Submitted Representative Baseline Fire EI to Ramboll
  Reviewed Future Fire Scenarios plan for sensitivity runs
    2 runs: wildfire FFS and Rx FFS
Workplan Tasks for the Next Two Months
  Finalize and approve FFS approach
  Execute FFS approach and deliver scenarios to Ramboll by 12/4/19
  Collect and collate data for SMP survey
  Add SMP survey data to WRAP map

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  Held an RBFFS call
  Ralph Morris of Ramboll attended call
Workplan Coordination Needed over the Next Two Months
  Mark Fitch will be coordinating with federal Rx burners to fill in a matrix of % increases in Rx burning by agency and region – Matt will scale the Rx FFS based on this matrix

## Slide 8: Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress Over the Last Month
  OGWG and Project Management Team (PMT) review and feedback
  Forecast (OTB & OTW) Inventory “Continuation of Historical Trends” – Complete
    Final Report and Inventory Spreadsheet including controls analysis
    SMOKE-inputs developed for WRAP Modeling and 2016 Emissions Platform Collaborative
  Tasks 2, 3, 4 – Underway
Workplan Tasks for the Next Two Months
  Task 2: Forecast 2028 Inventory (OTB & OTW) – November
    “Reduced Legacy Well Activity” and “Increased Horizontal Well Activity” Scenarios
    No additional controls analysis
  Task 3: Forecast 2028 Inventory (Additional Reasonable controls) – End of 2019
    Methodology by which emission control estimates may be made by regulatory agencies
  Task 4: Agency Program Review Task – End of 2019
    Emphasis on describing state programs with agency input

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring Over the Last Month
  October 1 – OGWG Webinar Midterm Update
  October 8 – OGWG Bi-Monthly Call
  October 15 & 30 – Project Management Team Calls
    Coordinate and PMT feedback with Ramboll
Workplan Coordination Needed Over the Next Two Months
  Nov. 12 – Project Management Team Call
  Dec. 10 – OGWG Bi-Monthly Call
  OGWG and PMT review and feedback on draft work products
    Mid-November: Forecast Scenarios Draft Final Report (3 scenarios included) & Spreadsheets
    November: Additional Reasonable Controls Report/Memo
    November: Agency Input to describe state programs
  Coordination with RHPWG Control Measures Subcommittee
Coordination (External to WRAP) Occurring / Needed
  EPA’s 2016 Modeling Platform Collaborative – availability of OGWG baseline & future inventory
  2017 NEI – account for inventory improvements

## Slide 11: Regional Technical Operations Work Group

## Slide 12: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  2014v2 base case simulation underway
  Presentation on “Modeling: International vs. US Contributions” at RHPWG ‘Octoberfest’ (10/3)
  Dynamic model evaluation scoping study
  Representative baseline EGU profiles
  Discussion of WRAP TSS2 analyses and graphics (10/17)

## Slide 13: Workplan Progress by RTOWG
Workplan Tasks for the Next Two Months
  Finish 2014v2 CAMx base case run
  Abbreviated fire plume rise sensitivity run
  GEOS-Chem/CAMx International Emissions (ZROW and Natural runs)
  Broad-Based Anthro vs. Natural PM Source Apportionment run
  Representative Baseline Emissions and PGM Modeling
  2028 Mobile Source and O&G Emissions Projections
  2028 OTB/OTW Modeling and Visibility Projections
  Analysis of OAQPS 2016 beta’ Regional Haze Modeling Platform & 2028 Visibility Projections

## Slide 14: Workplan Coordination Activities by RTOWG
Workplan Coordination Occurring over the Last Month
  Coordination with Ramboll on modeling progress (10/3, 10/10, 10/17)
  Monthly RTOWG call (10/15) – discussion on modeling products and updates on schedule
  EPA webinar on 2028 modeling (10/15)
  HAQAST ozone (10/2) and haze (10/17) monthly calls
  Calling in for OGWG (10/1), RHPWG (10/17)
  Bi-weekly RTOWG co-chair coordination calls

## Slide 15: Workplan Coordination Activities by RTOWG
Workplan Coordination Needed over the Next Two Months
  Extended RTOWG meeting in November (11/19) – discuss 2014v2 results
  Emission inventory updates for 2028: mobile, EGU’s
  Coordination calls with Ramboll for completion of Phase III modeling deliverables and preparing for Phase IV
  Preparation of representative baseline emissions
  HAQAST ozone and haze calls

## Slide 16: Regional Haze Planning Work Group

## Slide 17
Workplan Progress and Coordination over the Last Month
  October 3rd Milestone Webinar
  Review of EPA’s Regional Haze Guidance
Workplan tasks and Coordination for the Next Two Months
  Development of Regional Haze in the West Storyboard
  Coordinate ongoing discussions of controls and modeling – both require states to consult with sources
  WESTAR/WRAP Fall Business Meeting
Workplan Progress & Coordination by Regional Haze Planning Work Group

## Slide 18: Workplan Progress by Control Measures Subcommittee
Workplan Progress over the Last Month
  Call was held on September 23rd
  States in various stages of 4-factor analysis work
Workplan Tasks for the Next Two Months
  Next call October 31st –
    Plan to discuss BART/RP controls and costs from Round 1 WRAP RH SIPs
    Continue discussion on determining remaining useful life for EGUs considering retirement

## Slide 19: Workplan Coordination Activities by Control Measures Subcommittee
Workplan Coordination Occurring over the Last Month
  Participate on monthly O&G Workgroup calls
Workplan Coordination Needed over the Next Two Months
  Continue to coordinate with O&G work group and Emission Inventory Subcommittee on emission forecasts.

## Slide 20: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress over the Last Month
  Elevated Coordination Framework to RHPWG -> TSS
  Review of TSS FAQ Document & TSS Glossary
  TSSv2 Deliverables and New Products Presentation
  Overview of outstanding tasks
Workplan Tasks for the Next Two Month
  Continue overview of TSSv2 development
  Elevate FAQ and Glossary to RHPWG
  Revisit TSS Priorities document
  Mockup presentation of storyboard

## Slide 21: Workplan Coordination Activities by Coordination and Glide Path Subcommittee
Workplan Coordination Occurring over the Last Month
  The subcommittee coordinated with the following entities:
    TSS – Elevated Coordination Framework for Consensus
Workplan Coordination Needed over the Next Two Months
  RTOWG – Coordination on Natural Conditions Project findings and opportunities to model outcomes for future planning periods.
  RTOWG – TSS Priorities for Modeling/EI

## Slide 22
Workplan Progress by EI&MP Subcommittee
Workplan Progress over the Last Month
  Provided contractor with Representative Baseline emissions from states
  Received projection methodology for mobile sources (EPA Modeling Platform)
Workplan Tasks for the Next Two Months
  Obtain future facility emissions from states/locals and deliver to contractor.
    2028 OTW/OTB and Controls scenarios
  Contractor to start Rep. Baseline and OTW/OTB simulations

## Slide 23: Workplan Coordination Activities by EI&MP Subcommittee
Workplan Coordination Occurring over the Last Month
  Coordinated with contractor to review 2016 Modeling Platform release
Workplan Coordination Needed over the Next Two Months
  Representative baseline and future modeling scenarios require coordination as needed with O&G WG, contractor, Fire & Smoke WG,
  Coordinate with C&GP subcommittee to provide guidance to states on what is needed from them for the different modeling scenarios

## Slide 24
End of Workplan Progress Update