## Slide 1: Monthly Update on 2018-2019 WRAP Workplan February 27th, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2
Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last Month
  Factsheets, presentations completed.
  WRAP area Tribal/Environmental contact list – complete save R10
  Tribal Maps updated and reflected on WRAP main page map
  Oil and Gas report complete; contractor coordination with workgroups in progress
  Consultation and Coordination Protocol document, next attempt
Workplan Tasks for the Next Two Months
  Complete finalization by consensus of products under contract
  Prepare for webinars and National Tribal Forum on Air Quality

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  Consultation & Coordination (C&C) Subcommittee – ITEP/EN3 work under agreement for TDWG paused until future product procured through RHPWG contractor is drafted. Goal: product/s that fit into framework document and schedule; scheduling of webinars
  Oil and Gas Workgroup – ITEP, EN3 and TDWG drafted Tribal oil and gas related emissions
Workplan Coordination Needed over the Next Two Months
  Same groups as mentioned above
  EPA/NTAA/ITEP National Tribal Forum on Air Quality – breakout session and networking or tabling
  WRAP area Tribal contact list – complete R10

## Slide 5
Fire and Smoke Work Group
and

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  No new workplan updates for Round 2
  Josh Hall withdrew as co-chair; he got a new job
  Bob Kotchenruther (EPA Region 10) agreed to step in as co-chair; negotiating for a 3rd co-chair
  Convened the Representative Baseline and Future Fire Scenarios working group (RBFFS): had kick-off call, Matt Mavko briefed the group
Workplan Tasks for the Next Two Months
  Identify and implement methodologies to determine future year and multi-year baseline fire emissions for RH modeling: this is RBFFS’ main task
  RBFFS next call scheduled for March 6, will meet fortnightly

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  Member overlap between RBFFS and EIMP Subcommittee and RHWG
Workplan Coordination Needed over the Next Two Months
  Need to coordinate with Emissions Inventory and Modeling Protocol Subcommittee and RTOWG on preparing the baseline and future year fire EIs
  Currently coordinating with members of EIMP subcommittee
  Will coordinate with RTOWG when we get to Task 3 of RBFFS scope (Evaluate existing plume rise methods and recommend approaches for model implementation and sensitivity analyses)

## Slide 8
Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress over the Last Month
  OGWG Survey deliverables for O&G operator distribution by State Agencies
  OGWG Workplan Review & Update approved by consensus on Feb. 12 call and provided to TSC
Workplan Tasks for the Next Two Months
  OGWG O&G Operator Surveys – Mid-March - Completion
  Task 1: Base Year Inventory – Mid-March- Survey compilation memo
  Task 2: Forecast 2028 Inventory (On-the-books controls) – Late-February/Early-March - Forecast scenarios

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring over the Last Month
  February 12 – OGWG Bi-Monthly Call
    TDWG Contractor (EN3) Presentation – ITEP Task 1.4
  Assistance from Agencies/O&G operators to complete OGWG Survey
Workplan Coordination Needed over the Next Two Months
  March 4 – Project Management Team Call
    Discuss steps to wrap-up the survey effort with Ramboll.
    Coordinate on the forecast scenarios and provide PMT feedback to Ramboll.
  April 9 OGWG Bi-Monthly Call
    Agenda under development
  Assistance from remaining Agencies/O&G operators to complete OGWG Survey
  Additional coordination Tribal O&G EI and Outreach
  OGWG and PMT review and feedback on draft work products

## Slide 11
Regional Technical Operations Work Group

## Slide 12: Workplan Progress RTOWG
Workplan Progress over the Last Month
  The monthly RTOWG Call was held on February 12
    Joint call between RTOWG and RHPWG GP
    Presentation by Pat Brewer on Options for adjusting Uniform Rate of Progress Glide Path
    2014 Shakeout Western Modeling project deliverables and progress report
    Plans for updates to the RTOWG portion of the Workplan and request from revisions from the workgroup
    Request for comments on the Modeling Shakeout protocol.
  Bi-Weekly Western Modeling Shakeout Coordination call with Contractors occurred on January 31 and February 21
    Next Shakeout Coordination Call is March 6 at 9:30 AM MST
  RTOWG Co-Chairs call on February 19 discussed the workplan update especially Appendix E.
    The RTOWG Co-Chairs are “upping” the frequency of calls to every other week starting March 4
Workplan Coordination Occurring over the Previous Month
  RTOWG Co-Chairs Participated in the:
    RHPWG EI & MP call on January 31
    RHPWG call on February 5
    Joint RTOWG and RHPWG GP on February 12
    O&G WG Workplan call on February 12
    HAQAST Call update on the Ozone Background Analysis on February 6
Workplan Coordination over the Next Two Months
  Updated 2014 Base Year Emission Inventory from the RHPWG-EI MP
  Next “Shakeout” call with contractors is March 6 at 9:30 AM MST
  Next Regular Monthly RTOWG call is March 11 at 1:30 PM MST
  We need to do a joint call with the Fire and Smoke workgroup to discuss the emission inventory, projected emission inventory and plume rise-March
  Joint RTOWG and IWDW-WAQS coordination meeting to be held in Denver on April 2 to discuss the Modeling Shakeout results
  Discussion with EPA OAQPS on 2014 GEOS-CHEM simulation for use as boundary conditions

## Slide 13: Workplan Tasks for the Next Two Months: 2014 Platform Development and Shake-Out Study.
Highlighted are completed work elements as of February 20.
Last two weeks spent updating Modeling Plan and dealing with fire emissions
Contractor estimated that they are about two weeks behind schedule due to federal shut down

## Slide 14
Regional Haze Planning Work Group

## Slide 15: Workplan Progress by Regional Haze Planning Work Group
Workplan Progress over the Last Month
  Restructuring of Subcommittees
    Coordination and Glide Path
    Emissions Inventory and Modeling Protocols
    Control Measures
  Revisions to the table and tasks completed
Workplan tasks for the Next Two Months
  Most recent Draft report to go out before March 5th call
  Complete Subcommittee Restructuring
  Finalize draft report

## Slide 16: Workplan Coordination Activities by Regional Haze Planning Work Group
Workplan Coordination Occurring over the Last Month
  Coordination with all subcommittees to move work products through the consensus process
    TSS Website information
    Monitoring Data & Glide Path summary document
    Recommendations for Base Year Modeling
    Reasonable Progress Source Identification and Analysis Protocol
Workplan Coordination Needed over the Next Two Months
  Finalize consensus on WRAP Communication Framework
  Work with Coordination and Glide Path SC in planning for a Milestone Webinar in March to discuss monitoring data and control measures

## Slide 17: Coordination and Glide Path Subcommittee
Workplan Progress over the Last Month
  Consolidation of three subcommittees
  Consensus on TSS Website information
Workplan Tasks for the Next Two Months
  Consensus on WRAP Communication Framework
  Milestone Webinar in March to discuss monitoring data and control measures
Subcommittee Coordination
  Input from MDGP Subcommittee members on TSS v.2 data
  Coordinate with Control Measures SC for webinar
  Coordinate with Tribal Data to complete the Communication Framework

## Slide 18: Monitoring Data & Glide Path Tasks
Workplan Progress over the Last Month
  Subcommittee summary document has completed workgroup review
  Coordination with RTOWG on URP adjustment
  Contractor has finalized data substitution
Workplan Tasks for the Next Two Months
  Outline tasks for future contractor work on natural conditions
  Assist in upcoming monitoring data webinar
  Develop trend analysis methodology white paper
Subcommittee Coordination
  Members participate heavily in SDb Sc (past & future)
  Coordination with RTOWG on URP adjustment
  May increase interaction with EPA and with IMPROVE Subcommittee to develop method for determining Glide Path 2064 endpoint (future)

## Slide 19: Emissions Inventory and Modeling Protocol Subcommittee
Workplan Progress over the Last Month
  Finalized Recommendations for Base Year Modeling
Workplan Tasks for the Next Two Months
  Evaluate, Refine, and Process Base Year Inventory
  Finalize Emissions Representativeness for baseline forecasting
Subcommittee Coordination
  Coordination with RTOWG to complete the modeling shakeout
  Coordinating with RHPWG for consensus on work products

## Slide 20: Control Measures Subcommittee
Workplan Progress over the Last Month
  Reasonable Progress Source Identification and Analysis Protocol prepared for docketing
  Contractor working on q/D analysis
Workplan Tasks for the Next Two Months
  Finish q/D analysis
  Discuss q/D analysis work product on upcoming call
  Step down to bi-monthly calls after March call
Subcommittee Coordination
  EI&MP Subcommittee

## Slide 21
End of Workplan Progress Update

## Slide 22: Workplan Progress by (insert name) Work Group
Workplan Progress over the Last Month
  Example bullets
  Draft report out for review
  Provided feedback to contractor regarding IMPROVE data substitution
Workplan Tasks for the Next Two Months
  Example bullets
  Finalize draft report
  Review final contractor recommendations on data substitution

## Slide 23: Workplan Coordination Activities by (insert name) Work Group
Workplan Coordination Occurring over the Last Month
  Who did you coordinate with, what topics were discussed, and when did it occur (replace this text with you own)
Workplan Coordination Needed over the Next Two Months
  What activities do you need to coordinate on, with whom, and expected timeframe (replace this text with you own)