# **-- Monthly Coordination Call Agenda --**

# **Technical Steering Committee / Work Group Co-Chairs /**

# **RHPWG Subcommittee Leads**

May 29th, 2019 11:30 am – 1:00 pm PDT

Call in Number: **(800) 768-2983**

Access Code: **661 987 6342**

[Web Login](https://cc.callinfo.com/r/1r6phwcu37hrt%26eom) Call materials available on TSC webpage and WRAP calendar

* **Welcome, Roll Call, and Agenda Review (10 minutes) – Julie**

*Julie did role call*

* + Review and approve notes from March 27th call

*Review notes from Julie and send comments to Ryan and Julie*

* + TSC member updates

*Ryan Templeton ADEQ welcomed as new co-chair*

*Julie Oliver has joined as a new local representative*

* + Notes for this call – Richard Grimaldi
* **Work Group Status Reports (progress updates since April 25th) – (35 minutes)**
	+ WG Co-Chairs – 5 minutes each TDWG, FSWG, OGWG, & RTOWG – 10 minutes RHPWG

*Monthly updated provided – summaries can be found at:*

[**Monthly Workplan Progress Review**](https://www.wrapair2.org/pdf/19-05-29%20Monthly%20Workplan%20Progress%20Review.pptx)

*Additional Notes for RTOWG:*

*NGO using 2016 as base year for haze modeling. Group following these results and comparing to 2014 work. Phase 3 modeling - Close to having contract for phase 3 modeling. GEOS-CHEM run to be included to look at international emission. Fire plume rise sensitivity runs to be performed and updates to EI from shake out modeling. California has large dataset updates that will have a big impact. Developing a representative emission year. An EI relevant to haze planners to characterize emission updates. EGU will be included in representative year.*

*RHPWH (Jay) - Q/d analysis review done by subcontractor – follow link. Coordination for June 20th webinar underway and will include support from other WG. Getting consensus on communication plan. Storyboard to be created for RH in the west. Coordination on glidepath. Draft storyboard developed - to be used for outreach in stakeholder mtgs. EI modeling protocol - Ferran looking at 2028 strategies*

* **TSC Action Items (25 minutes)**
	+ Docket Announcements
		- [Completed Documents](http://wrapair2.org/TSC_Docket.aspx) (5 minutes) – Julie

*4 dockets completed (see doc march 29th) no questions or comments received on posted documents*

* + - New Documents for Docketing

*4 new dockets posted (6 files) comments/questions due June 26th.*

* + - * [Overview of Regional Haze Planning](http://wrapair2.org/pdf/Overview%20of%20RH%20Planning%20RHPWG%20consensus%20May7_2019.pdf) (5 minutes)
			* [Recommendations for Base Year Modeling](http://wrapair2.org/pdf/WRAP%20Regional%20Haze%20SIP%20Emissions%20Inventory%20Review%20Documentation_for_Docket%20Feb2019.pdf) (5 minutes)
			* [Tribal AQS Data Gap Study technical report, Tribal and Tribally-related air monitoring studies report](http://wrapair2.org/pdf/WRAP%20Task%201.2%20Report_11-23-18.docx), [spreadsheet](http://wrapair2.org/pdf/Tribal%20AQ%20Monitoring%20Sites_11.21.18.xlsx) (5 minutes)
			* [Tribal NEI Data Gap Study technical report, Tribe NEI Data Gap report](http://wrapair2.org/pdf/WRAP%20Task%201.3%20Report_DRAFT_12.14.18.docx), [spreadsheet](http://wrapair2.org/pdf/Copy%20of%20TribesWithPointSources.xlsx) (5 minutes)

Review of completed works on TSC webpage

* **TSC Administrative and Informational Items (20 minutes)**
	+ Informational Items
		- [Q/D Analysis tool and guidance memos](http://views.cira.colostate.edu/tssv2/Emissions/QDAnalysis.aspx) (10 minutes) – Curt

*Overview of work done with consultant (Ramboll). Based on 2014 NEI and screening of point sources. Default settings in spread sheet. Q/d set at 10. Ability to adjust Q/d. Some states lowering threshold in many cases as d tends to result in no sources. States need to manage the sources they are working with. Tool has tracking to view the emissions you’re seeing at the Class I areas. EPA guidance recommends 80% of emission impacts. Colorado used Q/d 10 and have 22 sources. Others states doing similar. New source categories like airports now showing up in the analysis. Sources (like airports) where you can’t reasonably control, they are being removed from the analysis by many States. Identify sources and look at 4 factor analyses with a goal of having analysis done by December 2019. Is it appropriate and cost feasible to require additional controls at these sources? These will be used in 2028 emission projections. Allows state to look at what other states are doing and interstate coordination. Provide transparency between stakeholders on the rationale why states have chosen a specific approach. States included within 400km of a WRAP class I area.*

* + - Hold the date (10 minutes) – Ryan & Tom
			* *6/20 RHPWG informational webinar – Fire emissions, O&G Survey Success, EI Projections, and State Q/d status update*

*Encourage attendance for this webinar*

* + - * *Modeling and Analysis Schedule – Tom*

*Approved SOW for base year modeling 2014 and coordination inputs from state. Results may be available for Sept Webinar. Scoping dynamic modeling analysis 2002-2014-2028 depending on pricing and effectiveness.*

**Next Steps and Wrap up (5 minutes) - Ryan**

* + Review next steps and action items from call

No action items

* + Next call – June 26th call, Wednesday 11:30 am – 1:00 pm PDT
		- Note taker, Kris Ray

# **Call Notetaking Schedule**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Call Date** | **Time (PT)** | **Name** | **Agency** | **Representing** | **Geography** |
| 5/29/2019 | 11:30am – 1pm | Richard Grimaldi | Pima Co DEQ | Local | Arizona |
| 6/26/2019 | 11:30am – 1pm | Kris Ray | Confederated Tribes, Colville Nation | Tribe | Washington |
| 7/31/2019 | 11:30am – 1pm | Phil Allen | Oregon DEQ | State | Oregon |
| 8/28/2019 | 11:30am – 1pm | Theresa Alexander | BLM | Fed | National |
| 9/25/2019 | 11:30am – 1pm | Jason Walker | NW Band, Shoshone Nation - Washakie Reservation | Tribal | Utah/Idaho |
| 10/30/2019 | 11:30am – 1pm | Bob Kotchenruther | EPA Region 10 | Fed | Pacific NW |
| 11/27/2019 | 11:30am – 1pm | Julie Oliver | Spokane Regional Clean Air Agency | Local | Washington |