## Slide 1: Monthly Update on 2018-2019 WRAP Workplan March 25th, 2020 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group
Status of Letter - Tom

## Slide 3: Fire and Smoke Work Group

## Slide 4: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  No workgroup calls since last TSC meeting
  FFS EI:
    Workgroup members sending Matt comments on draft final report on fire emissions inventory work for Regional Haze modeling.
    Matt sent Future Fire Scenario Wildfire and Rx EI data to Ramboll.
  FETS transition action plan:
    Received feedback from Nez Perce Tribe (thank you, Julie!)

## Slide 5: Workplan Progress by Fire and Smoke Work Group
Workplan Tasks for the Next Month
  Members to review draft EI report and send Matt feedback
  Matt will revise FETS Action Plan to include new plan to incorporate with IDW
  Draft a list of bullet points to summarize self assessment and outline the future of the workgroup
  Final workgroup call will be on April 6.

## Slide 6: Proposed Future Projects (same as last month)
Continuing quarterly calls for Fire and Smoke WG (draft bullets)
  Provide a venue for federal, state, and tribal fire and smoke people to discuss matters relevant across agencies
    Wildfire and Rx coordination across agencies and jurisdictions
    Documentation and data sharing for exceptional events due to wildfire or Rx burns
    Maintain a link between regional haze planning and operational fire and smoke people
    Emissions inventory approaches, remote sensing, and other technical issues involving air quality and fire and smoke

## Slide 7: Oil and Gas Work Group

## Slide 8: Workplan Progress by Oil and Gas Work Group
Workplan Progress over the Last Month
  OGWG review and feedback
  Final Revisions (CO & NM information changes): Task 2 – Forecast Scenario (OTB & OTW - Medium Emissions Scenario)
  Final Revisions (CO & NM information changes): Task 2 – Forecast Scenarios (OTB & OTW - Low and High Emissions Scenarios)
  TSC Docket: Task 4 - Agency Program Review
  Consensus Approval: Task 3 – Additional Reasonable Controls
Tasks for the Next Two Months
  OGWG Self-Assessment
  Coordination - Integration for WRAP OGWG Base and Future Year Emissions Inventories in National Collaborative Platform

## Slide 9: Proposed Future Oil and Gas Projects
Potential Additional Future Project/s
  OGWG input from members/advisors
    Extend period of performance Ramboll contract (e.g., state specific assistance)
    Annual compilation of agency program review (i.e., capture regulatory changes)
    Potential for contractor specific support needs as identified and funded
  Additional discussion planned April 14, 2020 OGWG Bi-Monthly Call
  Future OGWG Communication Calls (every 4 months)
    Track oil & gas sector and keep up to date via roundtable
    Topic specific updates (e.g., BLM analyses using WRAP/OGWG work products)
    Identify additional WRAP assistance

## Slide 10: Regional Technical Operations Work Group

## Slide 11: Workplan Progress by RTOWG Work Group
Workplan Progress over the Last Month
  Weekly co-chair coordination calls
  Weekly calls with Ramboll to keep track of modeling progress
  RTOWG call on 3/12
    Weighted Emissions Potential / Area of Influence (WEP/AOI) (discussed later)
    Review of white paper for future visibility projections (discussed later)
    Comments on model run specification sheets
    Roundtable discussion on future modeling exercises
  Continued transfer of modeling files to CIRA

## Slide 12: Workplan Progress by RTOWG Work Group
Workplan Tasks for the Next Two Months
  Future year (2028) CAMx simulations (see table)
  Future year (2028) CAMx source apportionment simulation
  Continue development of evaluation tools for emissions and model results
  Calculate and display 2028 Reasonable Progress Goals (RPG)
  Dynamic Model Evaluation

## Slide 13: RTOWG Remaining Workplan Tasks

## Slide 14: Finished Products: AOI/WEP Analysis

## Slide 15: Finished Products: Potential Procedures for Making 2028 Visibility Projections using the WRAP 2014 Modeling Platform

## Slide 16: Regional Haze Planning Work Group

## Slide 17: Workplan Progress by Regional Haze Planning Work Group
Workplan Progress over the Last Month
  No Large Work Group call in February/March
Workplan Tasks for the Next Two Months
Additional opportunity for refinement and state input by 7/1/2020 for another modeling run

## Slide 18: Workplan Coordination Activities by Regional Haze Planning Work Group
Workplan Coordination Occurring over the Last Month
  March 16th 2028PAC milestone
Workplan Coordination Needed over the Next Two Months
  Group meeting scheduled for April 7th
    RTOWG modeling update
    2028PAC summary by state and additional run
    Status update on May 19-20th meeting
    Mobile emissions project complete
    WRAP State RH Progress Website

## Slide 19: Workplan Progress by RH Planning Work Group – Control Measures Subcommittee
Workplan Progress over the Last Month
  February call discussion on providing emission reduction estimates to WRAP by March 16th deadline
  A few states (AZ, ND & NM) further along in the 4-factor review intend to provide emission reduction estimates for the 2028 control run
  Several states (CO, ID, MT, OR, UT, WA) further behind in the 4-factor review will likely rely on OTB/OTW reductions in the 2028 baseline
  Couple states (CA & NV) may provide emission reduction estimates
Workplan Tasks for the Next Two Months
  Next call on March 23rd
  States to continue 4-factor review work
  States to review WEP analysis when it becomes available

## Slide 20: Workplan Coordination Activities by RH Planning Work Group – Control Measures Subcommittee
Workplan Coordination Occurring over the Last Month
  none
Workplan Coordination Needed over the Next Two Months
  OGWG call participation

## Slide 21: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress for March
  TSS FAQ Document Finalized
  TSSv2 Delivery Update, Emission Tools, and WEP Presentation
  ARS Data Substitution and IMRPOVE December Patch Presentation
  Discussion on Interstate Transport Coordination
Workplan Tasks for the Next Two Month
  Continue oversight of TSSv2 development
  Gain consensus on TSS Glossary
  Support creation of RH Storyboard
  Testing of TSS tools

## Slide 22: Workplan Coordination Activities by Coordination and Glide Path Subcommittee
Workplan Coordination Occurring over the Last Month
  Coordination with CIRA
  Coordination with ARS
Workplan Coordination Needed over the Next Two Months
  Continued engagement with CIRA and ARS

## Slide 23: Workplan Progress by RHPWG EI&MP SC
Workplan Progress over the Last Month
  Compiled potential additional controls emissions inputs from states
  Shared info with states/locals about specs and progress on modeling
Workplan Tasks for the Next Two Months
  Reports on results of base & future year visibility, source apportionment modeling, and model performance evaluation
  RTOWG contractor-supported report on Reasonable Progress Goals
  RTOWG – contractor supported Weighted Emissions Potential (WEP) analysis that will provide WEP maps of source areas impacting each Class I area

## Slide 24: Workplan Coordination by RHPWG EI&MP SC
Workplan Coordination Occurring over the Last Month
  Coordinated with other states/agencies as needed to review/format potential additional controls emissions files.
Workplan Coordination Needed over the Next Two Months
  Coordinate with contractor to receive details and timeline of modeling progress and deliverables.
  Coordinate with contractor to transfer potential additional controls emissions files from states.

## Slide 25: Proposed Future Projects
Potential Additional Future Project
  Secondary additional controls simulation for 2028 Regional Haze period.
    Summer 2020 modeling work.
    Chance for states to get potential controls from 4-factor analysis into the WRAP RH modeling framework.

## Slide 26
End of Workplan Progress Update