## Slide 1: Monthly Update on 2018-2019 WRAP Workplan May 27th, 2020 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group
No Updates

## Slide 3: Fire and Smoke Work Group

## Slide 4: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Held final workgroup call on April 6.
  All deliverables submitted.
  Website being finalized.
Activities for the Next Two Months / Future
  Proposed specifications for fire activity data/emissions tracking system to follow from Tom and Matt Mavko.
  Hold Fire and Smoke discussion call on July 20.

## Slide 5: Oil and Gas Work Group

## Slide 6: Progress by Oil and Gas Work Group
Workplan Progress and Coordination
  OGWG Workplan Tasks Complete
Tasks over the Last Month
  OGWG Self-Assessment
  April 14, 2020 OGWG Bi-Monthly Call
  Coordination - Integration for WRAP OGWG Base and Future Year Emissions Inventories in National Collaborative Platform
Tasks for the Next Several Months
  OGWG transition communication and to potential additional future project(s)

## Slide 7: Proposed Future Oil and Gas Projects
Potential Additional Future Project/s
  OGWG input from members/advisors
    Extend period of performance Ramboll contract (e.g., state specific assistance)
    Annual compilation of agency program review (i.e., capture regulatory changes)
    Potential for contractor specific support needs as identified and funded
  Future OGWG Communication Calls (every 4 months)
    Track oil & gas sector and keep up to date via roundtable
    Topic specific updates (e.g., BLM analyses using WRAP/OGWG work products)
    Identify additional WRAP assistance
  Next Call August 11, 2020

## Slide 8: Regional Technical Operations Work Group

## Slide 9: Workplan Progress by RTOWG
Workplan Progress over the Last Month
  Weekly co-chair coordination calls
  Weekly calls with Ramboll to keep track of modeling progress
  RTOWG call on 4/29
    Ramboll modeling progress report
    Summary comparing 2028 Regional Haze projections using WRAP modeling results to date to EPA 2016-based results
    Overview of projections methods
    Review draft of May 19-20 WebEx/call agenda on TSS-delivered Regional Haze monitoring/emissions/PAC1 vs. OTB projections results

## Slide 10: Workplan Progress by RTOWG
Workplan Progress over the Last Month (cont’d)
  Updates to CA emission inventory
  2028 source apportionment spec sheet posted for comment
  Weighted emission potential (WEP) spec sheet updated

## Slide 11: Workplan Progress by RTOWG
Workplan Tasks for the Next Two Months
  Future year (2028) CAMx source apportionment simulation
  Continue development of evaluation tools for emissions and model results
  Calculate and display 2028 Reasonable Progress Goals (RPG)
  WRAP modeling meeting (online): June 23 & 25
    Use the TSS2 to review interpretation methods for haze modeling results
      Day 1: projections to 2028
      Day 2: evaluation of source apportionment, emission sensitivity, and WEP/AOI results
  Dynamic Model Evaluation

## Slide 12: Workplan Progress by RTOWG
Workplan Tasks for the Next Two Months (cont’d)
  Evaluation of future visibility projection methods
    EPA – default
    EPA – corrected for fire and dust impacts
    Modeled Most Impaired day (ModMID) – Use MID from modeled SO2 and Nox
    Greatest IMPROVE Sample Day Population (GISDP) – Choose days that 1) minimize fire & dust impacts and 2) have best model performance

## Slide 13: RTOWG modeling priorities

## Slide 14: RTOWG modeling priorities

## Slide 15: Workplan Coordination Activities by RTOWG
Workplan Coordination Occurring over the Last Month
  Ramboll
Workplan Coordination Needed over the Next Two Months
  Ramboll
  Other workgroups as needed for investigating/discussing model results

## Slide 16: Proposed Future Projects
Potential Additional Future Project/s
  In addition to the particulate source apportionment results for haze, we will also have ozone source apportionment using CAMx’s APCA (“Anthropogenic Precursor Culpability Assessment”) diagnostic tool. This should be of interest to air quality planners for helping to understand regional ozone behavior and potential for future mitigation.

## Slide 17: Regional Haze Planning Work Group

## Slide 18: Workplan Progress by Regional Haze Planning Work Group
Workplan Progress over the Last Month
April 7 call
  Round 1 2028 Potential Additional Controls summary of responses and next steps. States to submit by July 1, potential control inventory for an additional model run
  Mobile Source Emissions Inventory Projections final memo and deliverables
  WRAP State Regional Haze Progress Website
May 19-20 Virtual Workplan Completion meeting
  Focused on Monitoring and Inventory Data accessibility on the TSSv2
Workplan Tasks for the Next Two Months
July 2020
July 2020
Notes: 1) RTOWG modeling - Ralph Morris (Slides to be posted to the RHPWG website after call) Update/progress presentation
Round 1 2028 Potential Additional Controls summary and next steps - David and Tom (Slides to be posted after call) Responses received from states and state summary of data/changes.
July 1, 2020 deadline for states to submit “refined” (or initial if not done 3/16) for additional modeling sensitivity run
4) Mobile Source Emissions Inventory Projections project. (David/Jay/Tom) Final memo and deliverables available on project wiki page: Mobile Source Emissions Inventory Projections Project
5) WRAP State Regional Haze Progress Website (Amber)

## Slide 19: Workplan Coordination Activities by Regional Haze Planning Work Group
Workplan Coordination Occurring over the Last Month
  Group meeting scheduled for April 7th
    RTOWG modeling update
    Emissions Inventory Subcommittee
    Control Measures Subcommittee
  May 19th-20th Workplan Completion Webinar
    RTOWG
    TDWG
    FSWG
    RHPWG Subcommittees
Workplan Coordination Needed over the Next Two Months

## Slide 20: Workplan Progress by RH Planning Work Group – Control Measures Subcommittee
Workplan Progress over the Last Month
  April call – states provided updates on 4-factor review work
    Most states have received the requested source information and are reviewing source control options, feasibility and costs
    Many states are starting internal discussions on emission control costs and the appropriate cost effectiveness threshold
Workplan Tasks for the Next Two Months
  Next call on May 26th
  States to continue 4-factor review work
  States to review AOI and WEP analysis when it becomes available

## Slide 21: Workplan Coordination Activities by RH Planning Work Group – Control Measures Subcommittee
Workplan Coordination Occurring over the Last Month
  Participation on OGWG call
Workplan Coordination Needed over the Next Two Months
  OGWG call participation

## Slide 22: Proposed Future Projects by RH Planning Work Group – Control Measures Subcommittee
Potential Additional Future Project/s
  Depending on progress of emission control decisions, States considering whether an extra modeling analysis could be done over the summer or early fall
  Coordination with the Emissions Inventory and Modeling Protocol Subcommittee is necessary to estimate potential emission reductions and timing of modeling

## Slide 23: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress for April-May
  Group did not meet for May
  TSSv2 Delivery Update, Emission Tools, and WEP Presentation
  Storyboard status update
  ARS Data Substitution and EPA Patched Data Memo review
  Discussion on disseminating four factors to public.
Workplan Tasks for the Next Two Month
  Continue oversight of TSSv2 development
  Support creation of RH Storyboard
  Testing of TSS tools

## Slide 24: Workplan Coordination Activities by Coordination and Glide Path Subcommittee
Workplan Coordination Occurring over the Last Month
  Coordination with CIRA (TSS)
  Coordination with ARS (Data Substitution)
  Coordination with Ramboll (WEP)
Workplan Coordination Needed over the Next Two Months
  Continued engagement with CIRA, ARS, Ramboll

## Slide 25: Workplan Progress by RHPWG EI&MP SC
Workplan Progress over the Last Month
  Emissions loaded on TSS Express Tool
  Preparation for NEI tables to be added to TSS Express Tool
Workplan Tasks for the Next Two Months
  RTOWG contractor-supported reports and analyses
  Work with states to get PAC v2 submitted

## Slide 26: Workplan Coordination by RHPWG EI&MP SC
Workplan Coordination Occurring over the Last Month
  Coordinated with other states/agencies as needed to analyze emissions on TSS.
Workplan Coordination Needed over the Next Two Months
  Coordinate with contractor to get TSS emissions further updated.
  Coordinate with contractor to transfer potential additional controls v2 emissions files from states.

## Slide 27
End of Workplan Progress Update