# **-- Monthly Coordination Call Notes --**

# **Technical Steering Committee / Work Group Co-Chairs /**

# **RHPWG Subcommittee Leads**

February 26th, 2020 11:30 am – 1:00 pm PST, 12:30 pm – 2:00 pm MST

Call in Number: **800-768-2983**

Access Code: **661 987 6342**

[Web Login](https://cc.callinfo.com/r/1206mw2pcoskj%26eom) Call materials available on TSC webpage and WRAP calendar

* **Welcome, Roll Call, and Agenda Review (10 minutes) – Julie**

Attendees:

* + Reviewed and approve notes from January 29th call
* **Work Group Status Reports (progress updates since December 4th)**
	+ See PowerPoint presentation for more details
	+ TDWG
		- Calls in Dec 2019 and Feb 2020
		- Final review and adoption of a participation letter to encourage tribes to become active
		- EN3 oil and gas report reviewed and now on docket
		- Reviewed 2020 ITEP scope of work
		- Looked at workplan tasks over the next 2 months
		- Future includes maintaining the tribal contact list, ITEP work and outreach
	+ FSWG
		- Call on Feb 24
		- Future Fire Scenario EI draft final report out to the group
		- Prep for future wildfire and prescribed fire EI’s completed
		- FETS transition plan into IWDW platform is in progress
		- Reviewed final tasks in the workplan, including wildfire coordination between State/Tribal/Federal
		- Future includes reviewing the draft EI, revising the FETS action plan and continuing quarterly calls
	+ OGWG
		- Final revisions for Task 2 forecast scenarios for OTB and OTW, with CO and NM updates
		- Consensus approval on Feb 11 on Task 4
		- Working on consensus approval on Task 3 reasonable controls
		- Next 2 months will include a group self-assessment and coordination/integration of EI’s into national collaborative program
		- Potential future includes additional self-assessments of needs, member feedback by Mar 13 and call on Apr 14
	+ RTOWG
		- Weekly co-chair calls, plus weekly calls with Ramboll
		- Initial comparison done for 2014 v2 base case and representative baseline model results for IMPROVE for most impaired days
		- Have transferred modeling files to CIRA
		- Almost finished 2028 emissions processing
		- WEP/AOI analysis has started
		- Run Specification Sheets now available for review
		- Next 2 months will include future year 2028 CAMx simulations, continued development of evaluation tools, calculate 2028 reasonable progress goals, finish WEP/AOI analysis, dynamin model evaluation
	+ RHPWG
		- No large workgroup call in Feb
		- Next 2 months will include develop and refine 2028 forecasts, identification of 2028 emissions reductions from control strategies
		- CM Subcommittee:
			* Feb call discussed providing emissions reductions estimates to WRTAP by Mar 16
			* 4-factor reviews progress varies by State
			* Next 2 months includes continuing 4-factor review work, review WEP analysis
		- C&GP Subcommittee:
			* TSS FAQ document finalized
			* TSS v2 delivery update presentation
			* Next 2 months includes TSS v2 development, task prioritization, update the Storyboard
		- EI&MP Subcommittee:
			* Coordination and information sharing
			* Finalized the OTB/OTW emissions inputs
			* Next 2 months includes developing reports, reviewing RTOWG reports and analyses
* **TSC Action Items**
	+ New Docket items, open through 3/25
		- Summary of State Regulations Applicable to Oil and Gas Sources in the WESTAR-WRAP Region
		- O&G Control Requirements for NOx and VOCs in the WESTAR-WRAP region spreadsheet
		- Previously posted: EN3 Oil and Gas Report
			* Tribal AQS Data Gap Study
			* Tribal NEI Data Gap Study
			* Tribal Oil & Gas Emissions Inventory
	+ Advancement of Western Air Planning in the WRAP Document
		- No comments since the last call
		- TSC considers to be final, pending any WRAP Board changes
* **TSC Administrative and Informational Items**
	+ Future Project Scoping
		- Finalizing the scope of work for additional oil & gas modeling for BLM
		- List of modeling analyses possible for weight of evidence and prioritization
	+ WESTAR Spring Business Meeting (April 21-22)
		- Includes visibility trends, regional haze updates, 179B guidance, source apportionment for ozone, State outreach roundtable
	+ WRAP Meeting (April 23)
		- Includes workplan progress reports, regional haze planning tasks, workload and priorities
	+ WESTAR-WRAP Regional Haze Workplan Completion meeting (May 19-20)
		- Workgroup co-chairs will report on deliverables on May 19
		- Mapping results and tools on May 20
		- Agenda to come
		- WRAP will pay for travel for 1 person per State/Tribe
* **Next Steps and Wrap up**
	+ Review next steps and action items from call
		- Tom will clean up the docket
		- Please review docket items by the next call
		- Review WESTAR/WRAP meeting agendas and let Tom know if not going to be able to make it, issues, etc.
	+ Next call – March 25th, 2020
	+ Note taker, Melissa Hovey