# **-- Monthly Coordination Call Notes --**

# **Technical Steering Committee / Work Group Co-Chairs /**

# **RHPWG Subcommittee Leads**

February 26th, 2020 11:30 am – 1:00 pm PST, 12:30 pm – 2:00 pm MST

Call in Number: **800-768-2983**

Access Code: **661 987 6342**

[Web Login](https://cc.callinfo.com/r/1206mw2pcoskj&eom) Call materials available on TSC webpage and WRAP calendar

* **Welcome, Roll Call, and Agenda Review (10 minutes) – Julie**

Attendees:

* + Reviewed and approve notes from January 29th call
* **Work Group Status Reports (progress updates since December 4th)**
  + See PowerPoint presentation for more details
  + TDWG
    - Calls in Dec 2019 and Feb 2020
    - Final review and adoption of a participation letter to encourage tribes to become active
    - EN3 oil and gas report reviewed and now on docket
    - Reviewed 2020 ITEP scope of work
    - Looked at workplan tasks over the next 2 months
    - Future includes maintaining the tribal contact list, ITEP work and outreach
  + FSWG
    - Call on Feb 24
    - Future Fire Scenario EI draft final report out to the group
    - Prep for future wildfire and prescribed fire EI’s completed
    - FETS transition plan into IWDW platform is in progress
    - Reviewed final tasks in the workplan, including wildfire coordination between State/Tribal/Federal
    - Future includes reviewing the draft EI, revising the FETS action plan and continuing quarterly calls
  + OGWG
    - Final revisions for Task 2 forecast scenarios for OTB and OTW, with CO and NM updates
    - Consensus approval on Feb 11 on Task 4
    - Working on consensus approval on Task 3 reasonable controls
    - Next 2 months will include a group self-assessment and coordination/integration of EI’s into national collaborative program
    - Potential future includes additional self-assessments of needs, member feedback by Mar 13 and call on Apr 14
  + RTOWG
    - Weekly co-chair calls, plus weekly calls with Ramboll
    - Initial comparison done for 2014 v2 base case and representative baseline model results for IMPROVE for most impaired days
    - Have transferred modeling files to CIRA
    - Almost finished 2028 emissions processing
    - WEP/AOI analysis has started
    - Run Specification Sheets now available for review
    - Next 2 months will include future year 2028 CAMx simulations, continued development of evaluation tools, calculate 2028 reasonable progress goals, finish WEP/AOI analysis, dynamin model evaluation
  + RHPWG
    - No large workgroup call in Feb
    - Next 2 months will include develop and refine 2028 forecasts, identification of 2028 emissions reductions from control strategies
    - CM Subcommittee:
      * Feb call discussed providing emissions reductions estimates to WRTAP by Mar 16
      * 4-factor reviews progress varies by State
      * Next 2 months includes continuing 4-factor review work, review WEP analysis
    - C&GP Subcommittee:
      * TSS FAQ document finalized
      * TSS v2 delivery update presentation
      * Next 2 months includes TSS v2 development, task prioritization, update the Storyboard
    - EI&MP Subcommittee:
      * Coordination and information sharing
      * Finalized the OTB/OTW emissions inputs
      * Next 2 months includes developing reports, reviewing RTOWG reports and analyses
* **TSC Action Items**
  + New Docket items, open through 3/25
    - Summary of State Regulations Applicable to Oil and Gas Sources in the WESTAR-WRAP Region
    - O&G Control Requirements for NOx and VOCs in the WESTAR-WRAP region spreadsheet
    - Previously posted: EN3 Oil and Gas Report
      * Tribal AQS Data Gap Study
      * Tribal NEI Data Gap Study
      * Tribal Oil & Gas Emissions Inventory
  + Advancement of Western Air Planning in the WRAP Document
    - No comments since the last call
    - TSC considers to be final, pending any WRAP Board changes
* **TSC Administrative and Informational Items**
  + Future Project Scoping
    - Finalizing the scope of work for additional oil & gas modeling for BLM
    - List of modeling analyses possible for weight of evidence and prioritization
  + WESTAR Spring Business Meeting (April 21-22)
    - Includes visibility trends, regional haze updates, 179B guidance, source apportionment for ozone, State outreach roundtable
  + WRAP Meeting (April 23)
    - Includes workplan progress reports, regional haze planning tasks, workload and priorities
  + WESTAR-WRAP Regional Haze Workplan Completion meeting (May 19-20)
    - Workgroup co-chairs will report on deliverables on May 19
    - Mapping results and tools on May 20
    - Agenda to come
    - WRAP will pay for travel for 1 person per State/Tribe
* **Next Steps and Wrap up**
  + Review next steps and action items from call
    - Tom will clean up the docket
    - Please review docket items by the next call
    - Review WESTAR/WRAP meeting agendas and let Tom know if not going to be able to make it, issues, etc.
  + Next call – March 25th, 2020
  + Note taker, Melissa Hovey