Oil & Gas Work Group - Deliverables Tracking for Workplan Scope with survey questions

|  |  |  |
| --- | --- | --- |
| **OGWG Workplan Scope Deliverable** | **Prioritized list of Inputs needed / 2022 timing** | **Survey topics / questions** |
| Conduct annual survey of Oil and Gas-related air quality management needs | * Develop survey by April
* Reponses by July
* Compile results for Fall WESTAR-WRAP meeting (Sept.7-8)
 | * What changes has your agency made to manage and regulate emissions of upstream/midstream O&G sources in 2020-21? (please list for your jurisdiction)
	+ New/modified permit requirements?
	+ Emission inventory reporting?
	+ LDAR?
	+ other?
* What other agencies (federal, state, tribal) does your agency work with on upstream/midstream O&G issues? (please list and describe topics worked on)
* What are most important needs for your agency for O&G data and emissions mgmt. in 2022-23? (please rank)
	+ Addressing proposed federal rules?
	+ Modifying your agency’s rules and procedures for existing federal rules and state legislative mandates?
	+ Collecting and analyzing basic data for the upstream/midstream sector in your jurisdiction?
	+ other?
* What kind of support from the WRAP OGWG would benefit your agency the most? (please rank)
	+ Grants for regional work to benefit WRAP member agencies
	+ Technical virtual meeting discussions?
	+ Workshops up to 1 day in length?
	+ Detailed surveys?
	+ Discussing and drafting comments on rules and programs?
	+ Contractor-supported analysis through OGWG? (suggest funding options)
	+ other?
 |
| Improve emission inventories for the region and individual jurisdictions | * Report on 2020 NEI data inputs – April
* Develop priority list of O&G sources needing better inputs – consider:
	+ Speciation
	+ Geographic representativeness
	+ Appropriate/best activity data
	+ Jurisdictional and production type differences
* Compile summary for Fall WESTAR-WRAP meeting (Sept.7-8)
	+ Specify action items by state/tribal/federal agencies
 | * What emission inventory reporting and data analysis improvements has your agency made for upstream/midstream O&G sources in 2020-21? (please list)
	+ New/modified permit-required data reporting?
	+ Moved tracking of source activity from non-point to point?
	+ Expand scope of emission data reporting, e.g., added CH4?
	+ Developed new emissions estimate methods? Which processes?
	+ LDAR?
	+ Expand leak reporting based on better activity data, etc.?
	+ More complete / highly resolved spatial data?
	+ other?
* What are the most important EI-related needs for your agency for this sector in 2022-23? (please rank)
	+ Training?
	+ Operator surveys about engines, equipment, and practices?
	+ Technical discussion with other agencies?
	+ Contractor-supported analysis through OGWG? (suggest funding options)
	+ More resources for data collection and analysis?
	+ other?
 |
| Prepare annual assessment to track efforts to implement rules and control strategies, and report on compliance activities and emissions management structures | * Develop assessment input format survey by April
* Reponses by July
* Compile results for Fall WESTAR-WRAP meeting (Sept.7-8)
 | * *Use mgmt. survey responses above to help address.*
* What additional control programs/technology is your agency considering?
* Significant compliance activities over past few years to reduce O&G emissions (please list)
* Describe your agency’s approach to managing emissions
	+ Registration of sources
	+ Technology standards
	+ Permit requirement with controls and emissions reporting
	+ Combinations of these approaches (please explain)
	+ other?
 |