## Slide 1
2019
Spring
Summer
Fall
Continue regular stakeholder engagement on source screening and control measures
Continue stakeholder engagement on draft control plan
EPA consultation with tribes before acting on SIPs/TIPs
Begin formal comment period
Respond to comments, revise plan as necessary
Submit final SIP/TIP to EPA
State-tribal coordination on draft SIPs/TIPs
State-tribal coordination through EPA and for sources requiring controls on tribal lands
D R A F T
Begin regular stakeholder engagement on source screening and control measures
Host meeting with stakeholders to discuss steps taken to date, process moving forward, proposed control measures, projected visibility improvement
Timeline includes selected items from the WRAP Schedule of Communication described in the Consultation and Coordination Framework, with important tribal consultation and coordination milestones added
WRAP Regional Haze Planning Schedule of Communication
Indicates Significant Tribal C&C Milestone
2020
Winter
Spring
Summer
Fall
2021
Winter
Spring
Summer
Fall