## Resources
Resource | Link
2014 Shakeout v1 Emissions Changes - Summary Document | http://views.cira.colostate.edu/wiki/Attachments/2014v2_Review/WRAP%20Regional%20Haze%20SIP%20Emissions%20Inventory%20Review%20Documentation_Docket.docx
Western Regional Modeling Plan - March 27, 2019 Update | http://www.wrapair2.org/pdf/WesternModelingPlan%20update%20March27_2019.pdf
Guidance for submitting Representative Baseline Emissions | http://views.cira.colostate.edu/wiki/Attachments/2014v2_Review/WRAP%20RHPWG%20EIMP%20Representativeness%20Guidance%20March29.docx
Intermountain West Data Warehouse - granular modeling data | http://views.cira.colostate.edu/iwdw/Emissions/ | also | http://views.cira.colostate.edu/iwdw/Modeling/
WRAP TSS v2 (http://views.cira.colostate.edu/tssv2/) | emissions data and modeling results tools for air quality planners to be released soon

## Scenario Descriptions
| Emissions Submission Due Date | Modeing processing/run timeframe | Scenario Purpose
2014 Shakeout v1 | January 15, 2019 | Dec. 2018 through April 2019 | Test modeling platform
2014 Shakeout v2 | May 15, 2019 | May through July 2019 | Finalize modeling platform; fix issues found in v1
Current/Representative Baseline | June 20, 2019 | June through August 2019 | Represent current large facility emissions for comparison to future scenarios.
2028 OTW/OTB | August 1, 2019 | August through October 2019 | Represent future large facility emissions with expected "On-the-way" or "On-the-books" changes
2028 OTW/OTB Source Apportionment/Sensitivity/WEP | not applicable | October 2019 through early 2020 | Provide additional results of source category, species, and geographic area contributions for planning and consultation
2028 "potential additional" Controls | December 19, 2019 | January through March 2020 | Represent future large facility emissions with possible Emission Controls from 4-Factor Analysis

## Emissions Categories
Emissions Category | Emissions Sector | 2014 Shakeout v1 | 2014 Shakeout v2 | Representative Baseline | 2028 OTW/OTB | 2028 Controls
EGU Facilities | point | 2014 NEI v2 + State Updates | 2014 Shakeout v1 + State Updates | EGU project results / final state inputs |  | 2028 OTW/OTB + State Controls
non-EGU Facilities | point | 2014 NEI v2 + State Updates | 2014 Shakeout v1 + State Updates | 2014 Shakeout v2 + State Baseline | Representative Baseline + State OTW/OTB | 2028 OTW/OTB + State Controls
Oil & Gas Development | point | 2014 NEI v2 + State Updates | 2014 Shakeout v1 + State Updates | O&G Workgroup | O&G Workgroup, medium scenario | O&G Workgroup, choices by state
On-Road Vehicles | onroad | 2014 NEI v2 | (No Change) | (No Change) | Projections by modeling contractor with documentation | (No Change)
Non-Road Mobile | nonroad | 2014 NEI v2 | (No Change) | (No Change) | Projections by modeling contractor with documentation | (No Change)
Off-Shore Shipping | cmv | 2014 NEI v2 | (No Change) | (No Change) | Projections by modeling contractor with documentation | (No Change)
All Other Sources | nonpoint | 2014 NEI v2 + State Updates | (No Change) | (No Change) | Projections by modeling contractor with documentation | (No Change)
Soil & Vegetation | biogenic | MEGAN 3.0 | (No Change) | (No Change) | (No Change) | (No Change)
Wildfire | fire | 2014 NEI v2 | 2014 NEI v2 ? | Fire & Smoke WG | (No Change) | (No Change)
Rx & Ag Fires | fire | 2014 NEI v2 | 2014 NEI v2 ? | Fire & Smoke WG | (No Change) | (No Change)
Wind Blown Dust | N/A (separate module) | N/A (separate module) | (No Change) | (No Change) | (No Change) | (No Change)

## Source Apportionment
* 2008 Regional Haze Plan Source Apportionment (Will be updated for 2021 SIP)
PM Source Apportionment Technology (PSAT) tool for the attribution of sulfate and nitrate sources only.
Weighted Emissions Potential (WEP) tool for attribution of sources of sulfate, nitrate, organic carbon, elemental carbon, fine PM, and coarse PM.
PM Source Apportionment Categories | Weighted Emission Potential Categories
Point | Point
Area | Area
Area O&G
Off-Shore
Road Dust
Fugitive Dust
Wind-Blown Dust
Mobile | On-Road Mobile
Off-Road Mobile
Anthro. Fires | Anthro. Fires
Nat. Fires & Biogenics | Natural Fires
Biogenics