## Slide 1: Williston Basin O&G Emissions Inventory Project Status April 16, 2013
Tom Moore
WRAP Air Quality Program Manager
tmoore@westgov.org

## Slide 2: Background
Bureau of Land Management (BLM) Montana-Dakotas Office is sponsoring development of an oil and gas (O&G) emissions inventory for the Williston Basin in North Dakota, South Dakota, and Montana, and the Montana North Central (Great Plains) Basin
  The Western Regional Air Partnership (WRAP), with expert contractor assistance, will build and report the inventory using the WRAP Phase III methodology employed in large active basins in the intermountain West
  Result will be an accurate, comprehensive criteria pollutant inventory of actual emissions for most major point and area sources associated with exploration and production of O&G in the MT North Central (Great Plains) and ND-SD-MT Williston Basins for year 2011, as well as a mid-term projection year.
A benefit of the project is development of a more accurate regional O&G emission inventory data based on input from knowledgeable sources
  The project will also contribute to regional air quality modeling efforts and streamline future National Environmental Policy Act (NEPA) reviews by reducing the need for project-specific modeling.

## Slide 3: Project Description
WRAP project page: http://www.wrapair2.org/ND-SD-MT.aspx
Based on surveys of producers to update and gather data used to calculate emissions of the criteria pollutants – NOx, CO, VOCs, PM and SOx
WRAP’s contractors will coordinate participation and data collection from producers
  Survey data will be confidential and presented only in the aggregate
In parallel, the contractors will work with the air regulatory agencies (Montana Department of Environmental Quality - Air Resources Management Bureau, North Dakota Department of Health - Division of Air Quality, South Dakota Department of Environment and Natural Resources, and EPA Region 8) to verify and update emissions for permitted O&G point sources in the 2011 base year
Producer surveys will provide detailed area source data to supplement these point source data
Reviewing permitted point source data and applying the area source survey results will produce a comprehensive inventory of criteria pollutants covering most major O&G activities in each basin for four categories of mineral estate:
  1) federal
  2) trust (Indian allotted and tribal)
  3) state, and
  4) private (fee)
Work products consisting of a technical memorandum and spreadsheets will reside on the WRAP website. The project work will also include projections for each basin from the 2011 base year to a future year (2015, 2016, or 2017) based on input from BLM, producers, and air regulatory agencies.
Notes: The federal mineral estate will also include two (2) subparts, one associated with the decision space for National Forest System Lands, and the other with the decision space for lands under the jurisdiction of the BLM.

## Slide 4: Deliverables
Collection/analysis of producer survey results in each basin, based on information about number and type of equipment and activity levels;
Updated permitted point source data for each basin;
Basin-, tribal-, and county-level criteria pollutant emissions inventory data for 2011 and future projection year, and
Comprehensive regional criteria pollutant emissions for the O&G sector

## Slide 5: Revised Project Schedule for MT-Dakotas O&G Emissions Inventory Project – February 27, 2013 update
Part 1: Outreach | 
Prepare Surveys, Ranked List of Companies, Query for State/Federal Agencies, Access IHS database at BLM, identify Contacts from Ranked List of Operators from Production Statistics, Contacts from Agencies | November 2012 early December
Schedule and Hold Outreach Calls/Meetings | December 2012/January 2013
Distribute Survey Instruments and Agency Queries | early March
Agencies Complete/Submit Query Response | March 31st
Williston Basin Future Projections Workshop with Operators and BLM | Week of April 15th
Companies Complete/Submit Survey Instruments | May 7th
Part 2: Emission Inventory Compilation | 
BLM Provides Future Projection Inputs for Montana Great Plains Basin | Week of May 20
Compile Survey and Query Data | May 24th
Complete Emission Calculations and Draft Reports/Spreadsheets | July 10th
Report Review & Comment | July 24th
Complete Final Reports/Spreadsheets | August 7th
Prepare Stakeholder Summary | August 15th
Hold Stakeholder Review Calls | August 30th

## Slide 6: Seeking participation for most representative Basin-wide data
WILLISTON BASIN TARGET PARTICIPATING COMPANIES 2011 PRODUCTION STATISTICS |  |  |  | 
 | Company Name | % of Basin Oil Production | % of Basin Gas Production | % of Basin Well Count
1 | BRIGHAM OIL & GAS L P | 4 | 3 | 1
2 | BURLINGTON RESOURCES / CONOCO-PHILLIPS | 6 | 4 | 4
3 | CITATION OIL & GAS CORPORATION | 0 | 0 | 1
4 | CONTINENTAL RESOURCES INCORPORATED | 13 | 19 | 8
5 | DENBURY ONSHORE LLC | 5 | 4 | 9
6 | ENDURO OPERATING LLC | 0 | 0 | 1
7 | ENERPLUS RESOURCES (USA) CORPORATION | 3 | 3 | 2
8 | EOG RESOURCES INCORPORATED | 10 | 5 | 4
9 | FIDELITY EXPLORATION & PRODUCTION CO | 1 | 9 | 11
10 | G3 OPERATING LIMITED LIABILITY CORP | 0 | 0 | 1
11 | HESS CORPORATION | 8 | 14 | 6
12 | KODIAK OIL & GAS USA INCORPORATED | 2 | 2 | 1
13 | MARATHON OIL COMPANY | 4 | 3 | 2
14 | MUREX PETROLEUM CORPORATION | 2 | 1 | 2
15 | NEWFIELD PRODUCTION COMPANY | 2 | 2 | 1
16 | OASIS PETROLEUM NORTH AMERICA LLC | 3 | 2 | 2
17 | OXY USA INC | 2 | 1 | 1
18 | PETRO HARVESTER OPERATING CO LLC | 0 | 0 | 1
19 | PETRO-HUNT LLC | 3 | 4 | 3
20 | SEQUEL ENERGY LLC | 0 | 1 | 2
21 | SLAWSON EXPLORATION COMPANY INCORPOR | 4 | 2 | 2
22 | SM ENERGY COMPANY | 2 | 2 | 3
23 | TAQA NORTH USA INCORPORATED | 0 | 0 | 1
24 | WHITING OIL & GAS CORPORATION | 9 | 6 | 5
25 | WILLISTON HUNTER ND LLC | 0 | 0 | 1
26 | WPX Energy | 2 | 1 | 0
27 | XTO ENERGY INCORPORATED | 4 | 4 | 3
28 | ZENERGY INCORPORATED | 1 | 1 | 1
 | Percentage Representation for All Target Companies | 90 | 93 | 79
 | Percentage Representation Currently Committed to Supply Survey Data | 36 | 36 | 31

## Slide 7: Contacts
Tom Moore WRAP tmoore@westgov.org 970-491-8837
Amnon Bar-Ilan ENVIRON abarilan@environcorp.com 415-899-0700
Lee Gribovicz Airstar Consulting lg@westgov.org 307-333-1527
Susan Bassett BLM MT-Dakotas Office sbassett@blm.gov 406-896-5029